## Route53_Resolver_Project_Tasks
Task ID | Task Description | Owner/Team | Status | Priority | Dependencies | Notes
T1 | Create dedicated DNS VPC & associated resources | Cloud team | Not Started | High |  | Use AWS Quick Start or console; ensure high availability with multi-AZ subnets
T1.1 | Create Subnets (public and private for high availability) | Cloud team | Not Started | High | T1 | At least 2 subnets in different AZs for endpoints
T1.2 | Configure Network ACLs (NACLs) to allow DNS traffic (UDP/TCP port 53) | Cloud team | Not Started | High | T1.1 | Allow ephemeral ports for responses
T1.3 | Create Security Groups for DNS traffic (allow inbound/outbound UDP/TCP port 53 from/to relevant CIDRs) | Cloud team | Not Started | High | T1.1 | Reference CIDRs: on-prem, participating VPCs; least privilege
T2 | Create Resolver endpoints | Cloud team | Not Started | High | T1 | Ensure endpoints in private subnets
T2.1 | Create Outbound endpoint (in DNS-VPC subnets, associate security group) | Cloud team | Not Started | Medium | T2 | Target: on-prem DNS IPs
T2.2 | Create Inbound endpoint (in DNS-VPC subnets, associate security group) | Cloud team | Not Started | Medium | T2 | Security group allows from on-prem and participating VPCs
T3 | Create Forwarding rules | Cloud team | Not Started | Medium | T2 | Use Route 53 console or CLI
T3.1 | Rule 1: Forward DNS queries for zone onprem.private to on-premises DNS server IPs via outbound endpoint | Cloud team | Not Started | Medium | T3 | Requires outbound endpoint
T3.2 | Rule 2: Forward DNS queries for zone awscloud.private to the IP addresses of the resolver inbound endpoint | Cloud team | Not Started | Medium | T3 | For cross-account resolution
T4 | Associate the forwarding rules with DNS-VPC (for onprem.private rule) | Cloud team | Not Started | Medium | T3 | Only for onprem.private rule; awscloud.private not associated locally
T5 | Verify connectivity between on-premises and DNS-VPC (via VPN/Direct Connect) | Cloud team | Not Started | Medium | T1 | Test ping/traceroute or DNS query
T6 | Share forwarding rules with participating accounts using AWS Resource Access Manager (RAM) | Cloud team | Not Started | Medium | T3.2 | Centralized account action
T6.1 | Share with entire AWS Organization or specific accounts | Cloud team | Not Started | Medium |  | Prefer organization-wide sharing
T7 | Accept Shared Forwarding Rules in participating accounts | Cloud team | Not Started | Medium | T6 | Via RAM console
T7.1 | This step not required if rules shared with entire AWS Organization | Cloud team | Not Started | Low |  | Automated if org-shared
T7.2 | Associate Forwarding Rules with VPCs in each participating account | Cloud team/DevSecOps team | Not Started | Low | T6.1 | Via Route 53 console or CLI
T8 | Create Private hosted zones in each participating account | DevSecOps team | Not Started | Low | T7 | Unique per account to avoid conflicts
T8.1 | Create unique subdomain (e.g., acc1.awscloud.private) and associate with local VPCs | DevSecOps team | Not Started | Low | T7 | CLI: create-vpc-association-authorization
T8.2 | Create VPC association authorization for DNS-VPC using AWS CLI | DevSecOps team | Not Started | Low | T8.1 | CLI: associate-vpc-with-hosted-zone
T9 | Associate the private hosted zone with DNS-VPC (in centralized account, accept authorization using AWS CLI) | Cloud team | Not Started | Low | T8 | Requires on-prem connectivity
T9.1 | Configure on-premises DNS forwarders | On-prem team | Not Started | Low | T1, T5 | Requires VPN/Direct Connect
T9.2 | Set conditional forwarders on on-premises DNS server to forward awscloud.private queries to inbound endpoint IPs | On-prem team | Not Started | Low |  | Verify with nslookup from on-prem host
T10 | Test First Use Case: Resolving on-premises domains from AWS workloads | DevSecOps team / Cloud team | Not Started | Low | T9.2 | e.g., Resolve host1.onprem.private from AWS workload
T11 | Test Second Use Case: Resolving AWS private domains from on-premises workloads | DevSecOps team / Cloud team | Not Started | Low | T9.1 | e.g., Resolve host1.acc1.awscloud.private from on-prem
T12 | Test Third Use Case: Resolving private domains between AWS accounts | DevSecOps team / Cloud team | Not Started | Low | T9.2 | e.g., Resolve host2.acc2.awscloud.private from acc1
T13 | Document setup, including additional considerations (e.g., local resolution for PrivateLink, EFS) | Project team | Not Started | Low | All tests | Include limitations from blog (e.g., 10k QPS limit)
T14 | Set up monitoring and logging for Route 53 Resolver (e.g., query logging) | Cloud team | Not Started | Low | T12 | Enable Resolver query logging to CloudWatch
T15 | Consider implementing Route 53 Profiles for scalable management (per blog update) | Cloud team | Not Started | Low | T1 | Per March 31, 2025 blog update; simplifies multi-account setup